## Gantt Data
ID | Task Name | Start | End | Duration | Progress % | Dependency | Resources | Color
1 | Research & Workshops | 2026-01-16 | 2026-01-25 | 10 | 100 | - | All Team | Phase-Planning
2 | System Architecture | 2026-01-22 | 2026-01-28 | 7 | 100 | 1 | Tech Lead | Phase-Planning
3 | Data Pipeline Setup | 2026-01-27 | 2026-02-08 | 13 | 80 | 2 | Backend | Phase-Development
4 | Security Framework | 2026-01-29 | 2026-02-02 | 5 | 80 | 2 | DevOps | Phase-Development
5 | Agent Core Development | 2026-01-31 | 2026-02-20 | 21 | 65 | 3 | AI/ML | Critical
6 | API & UI Development | 2026-02-05 | 2026-02-22 | 18 | 60 | 5 | Frontend | Phase-Development
7 | Explainability Module | 2026-02-08 | 2026-02-22 | 15 | 55 | 5 | AI/ML | Phase-Development
8 | System Integration | 2026-02-19 | 2026-03-03 | 13 | 40 | 6,7 | Tech Lead | Critical
9 | Model Evaluation | 2026-02-24 | 2026-03-10 | 15 | 30 | 8 | AI/ML | Critical
10 | Pitch Preparation | 2026-03-02 | 2026-03-13 | 12 | 10 | 9 | All Team | Phase-Delivery
11 | Preliminary Submission (Milestone) | 2026-02-10 | 2026-02-10 | 0 | 100 | 5 | All Team | Milestone
12 | Preliminary Result (Milestone) | 2026-02-27 | 2026-02-27 | 0 | 0 | 8 | Organizer | Milestone
13 | Final Presentation (Milestone) | 2026-03-28 | 2026-03-28 | 0 | 0 | 10 | All Team | Milestone